## (NEEDS REWORK) -High Level Plan (hidden)
Hypervisor Bringup Plan - Initial
Vector Items | Tasks | Primary RTL Owner | DV Owner | Units | FE RTL support/date | MC RTL support/date | LS RTL | CSRs support required? | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar
[9 empty] | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Bringup Tests |  | Multiple |  | FE, MC, LS, CSRs
| HS-mode, access HS-CSRs, VS-CSRs and S-CSRs (like before) |  |  |  | Yes/<> | Yes/<> | NA | Yes | bar: Sep 38 to Sep 40
| (MP)V=1, VS-mode, HGATP.MODE=BARE, Trap (Exit VM) |  |  |  | Yes/<> | NA | Yes/<> | Yes | bar: Sep 38 to Sep 40
| (MP)V=1, VU-mode, HGATP.MODE=BARE, Trap (Exit VM) |  |  |  | Yes/<> | NA | Yes/<> | Yes | bar: Sep 39 to Sep 40
| V=1, VS-mode, access sstatus CSR with its vstatus address(Exception) |  |  |  | Yes/<> | NA | NA | Yes | bar: Sep 39 to Sep 40
| V=1, VS-mode, access sstatus CSR with supervisor csr address(No Exception) |  |  |  | Yes/<> | NA | NA | Yes | bar: Sep 39 to Sep 40
| M->VS, VU |  |  |  | Yes/<> | Yes/<> | NA | Yes | bar: Sep 39 to Sep 40
| HS->VS,VU |  |  |  | Yes/<> | NA | Yes/<> | Yes | bar: Sep 39 to Sep 40
| VS->VU |  |  |  | Yes/<> | NA | NA | Yes | bar: Sep 39 to Sep 40
| mstatus.TVM=1, read/write hgatp (Illegal instruction exception) |  |  |  | Yes/<> | NA | NA | Yes
2-Stage Translation |  | Deepak? |  | LS, MC | bar: Nov 45 to Feb 8
| Basic pagetable walk with guest pagetables enabled (sv57) |  |  |  | ? | ? | Yes/<> | Yes
| All guest paging modes (HGATP.MODE=sv48/39) |  |  |  | ? | ? | Yes/<> | Yes
| Guest pagefaults |  |  |  | w | Yes/<> | Yes/<> | Yes
| Hypervisor LdSt instructions (HLV, HLVX.HU/VU, HSV) |  |  |  | Yes/<> | Yes/<> | Yes/<> | Yes
| PMP crossing | [5 empty] | Yes/<>
FENCEs |  | Miles, Deepak |  | MC, LS | bar: Nov 46 to Dec 50
| SFENCE.VMA (v=0) |  |  |  | Yes,supported | NA | Yes/<>
| SFENCE.VMA (v=1) |  |  |  | Yes,supported | NA | Yes/<>
| HFENCE.VVMA |  |  |  | Yes/<> | NA | Yes/<>
| HFENCE.GVMA |  |  |  | Yes/<> | NA | Yes/<>
Traps |  | Max, Manan? |  | FE, MC | bar: Sep 38 to Dec 53
Virtual instruction exception (hcounteren)
| ECALL from VU/HS/VS |  |  |  | Yes/<>
| Trap delegation |  |  |  |  | Yes/<> |  | Yes
| Delegate HS/U trap => HS (medeleg/mideleg) |  |  |  |  | Yes/<> |  | Yes
| Delegate VS/VU trap => HS (medeleg/mideleg) |  |  |  |  | Yes/<> |  | Yes
| Delegate VS/VU trap => VS (hedeleg/hideleg) |  |  |  |  | Yes/<> |  | Yes
Transformed Instructions
Interrupts |  | Max? |  | MC, LS | bar: Nov 46 to Jan 4
HVIP => VS level interrupts (interrupt injection)
VSEIP: external interrupt
VSTIP: timer interrupt
VSSIP: software interrupt
IOMMU support
CSRs |  | Max? |  | MC, LS, CSRs | bar: Sep 38 to Nov 46
| henvcfg, henvcfgh | [6 empty] | Yes | bar: Sep 38 to Nov 46
| hstatus.HU/SPVP/SPV/GVA/VSBE | [6 empty] | Yes
| htimedelta/htimedeltah | [6 empty] | Yes
| htval | [6 empty] | Yes
| htinst | [6 empty] | Yes
Nested Virtualization
TBD

## SSU64XL
Scenario details
Scenario ID | Scenario Category | Scenario description | Additional details on scenarios | Pseudo Ops V2 | Notes
SID_SSU64XL_01 | Regular CSR Check | Covers WARL behaviour of MSTATUS.UXL/SSTATUS.UXL == 0b10 (Must have U mode) Read mstatus/sstatus.UXL 0b10, verify it is 0b10 | Works best if test is ran from U mode | # Read mstatus.UXL field mstatus_val = CsrRead(csr_name="mstatus", direct_read=True) # Extract UXL field (bits 33:32) uxl_mask = LoadImmediateStep(imm=0x300000000) # bits 33:32 uxl_extracted = Arithmetic(op="and", src1=mstatus_val, src2=uxl_mask) # Right shift by 32 bits to get UXL value shift_amount = LoadImmediateStep(imm=32) uxl_value = Arithmetic(op="srl", src1=uxl_extracted, src2=shift_amount) # Expected value is 0b10 (2) expected_uxl = LoadImmediateStep(imm=2) assert_uxl = AssertEqual(src1=uxl_value, src2=expected_uxl) # Read sstatus.UXL field sstatus_val = CsrRead(csr_name="sstatus", direct_read=True) # Extract UXL field (bits 33:32) uxl_extracted_s = Arithmetic(op="and", src1=sstatus_val, src2=uxl_mask) # Right shift by 32 bits uxl_value_s = Arithmetic(op="srl", src1=uxl_extracted_s, src2=shift_amount) # Verify it is also 0b10 assert_uxl_s = AssertEqual(src1=uxl_value_s, src2=expected_uxl) | Per Andrew Waterman - https://github.com/riscv/riscv-profiles/issues/75#issuecomment-1363439616 - U mode + RV64 should have UXL bit hardcoded to 0b10
SID_SSU64XL_02 | Virtualized CSR Check | Covers WARL behavior of VSSTATUS.UXL/HSTATUS.UXL == 0b10 Read vsstatus.uxl/hstatus/uxl, verify it is 0b10 | Works best if test is ran from U mode. Can only be ran in virtualized/hypervisor mode | # Read vsstatus.UXL field vsstatus_val = CsrRead(csr_name="vsstatus", direct_read=True) # Extract UXL field (bits 33:32) uxl_mask = LoadImmediateStep(imm=0x300000000) # bits 33:32 uxl_extracted_vs = Arithmetic(op="and", src1=vsstatus_val, src2=uxl_mask) # Right shift by 32 bits shift_amount = LoadImmediateStep(imm=32) uxl_value_vs = Arithmetic(op="srl", src1=uxl_extracted_vs, src2=shift_amount) # Expected value is 0b10 (2) expected_uxl = LoadImmediateStep(imm=2) assert_uxl_vs = AssertEqual(src1=uxl_value_vs, src2=expected_uxl) # Read hstatus.UXL field (bits 33:32) hstatus_val = CsrRead(csr_name="hstatus", direct_read=True) uxl_extracted_h = Arithmetic(op="and", src1=hstatus_val, src2=uxl_mask) uxl_value_h = Arithmetic(op="srl", src1=uxl_extracted_h, src2=shift_amount) # Verify it is also 0b10 assert_uxl_h = AssertEqual(src1=uxl_value_h, src2=expected_uxl)
SID_SSU64XL_03 | UXL bit check | underflow CSR and do 64 checks with SRLI, verifiying LSB is bit 1 (except after the 64th bit, where it is bit 0) | Works best if test is ran from U mode | # Load a register with maximum 64-bit value test_val = LoadImmediateStep(imm=0xFFFFFFFFFFFFFFFF) # Loop 64 times, shifting right and checking LSB for i in range(64): # Shift right logical by i positions shift_amt = LoadImmediateStep(imm=i) shifted = Arithmetic(op="srl", src1=test_val, src2=shift_amt) # Extract LSB (bit 0) lsb_mask = LoadImmediateStep(imm=1) lsb = Arithmetic(op="and", src1=shifted, src2=lsb_mask) # Expected value: 1 for bits 0-63, 0 for bit 64+ if i < 64: expected_lsb = LoadImmediateStep(imm=1) else: expected_lsb = LoadImmediateStep(imm=0) assert_lsb = AssertEqual(src1=lsb, src2=expected_lsb)

## Hypervisor_Interrupts (hidden)
Scenario details | [6 empty] | Dependencies - Timelines (Except RTL, rest of the fields to be filled in by dependent teams; Sample details filled in for example purpose) |  |  | Development Status (filled in by TP team) |  |  | Regression Status (auto-populated)
Scenario ID | Scenario Category | Scenario description | Additional details on scenarios | Stimulus Type | Coverage Type | Details on Dependency | RTL (Comes from "Milestone and Metrics Excel sheet - Bringup Tracker") | Unit TB | Dependency | Stimulus | Coverage | Bringup | Stimulus | Coverage
SID_HINTR_001 | 1. Direct/Vectored Virtual Interrupts | Cover Interrupt handling serviced to a direct/vectored address location for VS-interrupts | 1. Priv_Mode = {HS,VS,VU} 2. if delegation to VS-mode = {Off}: (i) stvec[1:0] =pick_all{00 : Direct, 01 : Vectored} Check sscause.msb =1 (interrupts) 2. if delegation to VS-mode = {On}: (i) vstvec[1:0] =pick_all{00 : Direct, 01 : Vectored} Check scause.msb =1 (interrupts) equivalent to checking vscause Randomise with pick_all{ xcause.randomise X xstvec[00,01] X xie X xip X Modes X xtatus.sie X hideleg(0,1) } | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_002 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from M-mode w/ & w/o delegation | 1. Interrupt remains pending due to corresponding delegation i.e. default Mideleg.[12,10,6,2] = [1,1,1,1] from M-mode to HS-mode. Randomize with (i) global interrupt enable = pick_all{sstatus.sie =1,0} (ii) local interrupt enable = pick_all{[hie.sgeie, hie.vseie, hie.vssie, hie.vstie] = (0,1)} (ii) interrupt pending = pick_all[hip.sgeip, hip.vseip, hip.vssip, hip.vstip] ={0,1} using all ways of interrupt generation (iii) Delegation = pick_all {hideleg.[10,6,2] = (0,1)} | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_003 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from HS-mode with both global & local interrupt enabled w/o delegation to VS-mode. | 1. Interrupt is serviced : (i) global interrupt enable i.e. sstatus.sie =1 (ii) && local interrupt enable i.e. [pick_any{hie.sgeie, hie.vseie, hie.vssie, hie.vstie} =1] (iii) with corresponding interrupt pin pending i.e. [pick_any{hip.sgeip, hip.vseip, hip.vssip, hip.vstip}=1] 2. No Delegation to VS-mode : Hideleg.[10,6,2] = {0,0,0} 3. Check Scause [12,10,6,2] Randomize with Interrupt generation(VSEIP/VSTIP read only in hip, VSSIP - R/W) (i) VSEIP = pick_one_or_more_at_time{write hvip.VSEIP ¦¦ bit of hgeip selected by hstatus.VGEIN ¦¦ platform-specific signal(external)} (ii) VSSIP = pick_all( write hvip.VSSIP, write hip.VSSIP) (iii) VSTIP = pick_one_or_more_at_time{write hvip.VSTIP ¦¦ platform-specific signal(timer)} (iv) SGEIP = hip.sgeip is read only = bitwise-logical OR [ hgeip.i && hgeie.i ] . If GEILEN is nonzero, GEILEN:1 is writable in hgeie, GEILEN_max = 63. Hstatus.VGEIN selects interrupt(i) in hgeip.i. hgeie selects the subset of GEI that cause a SGEI(HS-level) doesn't affect VSEIP generated using hgeip.i Bringup: pick{hie.vseie = 1, write hvip.vseip=1 --> hip.vseip (Read only), sstatus.sie = 1, Mode =HS, hideleg.vseip = 0} Note: VS-level interrupts & guest external interrupts are always delegated past M-mode to HS-mode (i.e Mideleg.[12,10,6,2] = [1,1,1,1] Note2: SGEI cannot be delegated to VS-mode (hideleg.12 = 0 always) | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded, Generation is left
SID_HINTR_004 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from HS-mode with global interrupt enabled but local interrupt disabled w/o delegation to VS-mode. | 1. Interrupt remains pending due to corresponding local interrupt disable i.e. [hie.vs*ie ¦¦ hgeie.i/hie.sgeie ]= 0 with global interrupt enable i.e. sstatus.sie =1 2. No Delegation to VS-mode : Hideleg.[10,6,2] = {0,0,0} Randomize with (i) interrupt pending = pick_all{hip.sgeip, hip.vseip, hip.vssip, hip.vstip} using all generation methods of all 4 interrupts. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_005 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from HS-mode with global interrupt disabled w/o delegation to VS-mode. | 1. Interupt remains pending due to global interrupt disable i.e. sstatus.sie =0 2. No Delegation to VS-mode : Hideleg.[10,6,2] = {0,0,0} Randomize with (i) interrupt enable = pick_all{hie.sgeie, hie.vseie, hie.vssie, hie.vstie} (ii) interrupt pending = pick_all{hip.sgeip, hip.vseip, hip.vssip, hip.vstip} using all generation methods of all 4 interrupts | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_006 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from VS/VU/HU-mode with local interrupt enabled w/o delegation to VS-mode. | 1. Interrupt is serviced in HS-mode: (i) irrespective of global interrupt enable i.e.pick_all{sstatus.sie=0,1} (ii) && local interrupt enable i.e. [pick_any{hie.sgeie, hie.vseie, hie.vssie, hie.vstie} =1] (iii) with corresponding interrupt pin pending i.e. [pick_any{hip.sgeip, hip.vseip, hip.vssip, hip.vstip}=1] 2. No Delegation to VS-mode : Hideleg.[10,6,2] = {0,0,0} 3. Check Scause [12,10,6,2] Randomize with (A) Priv_Mode = pick_all{VS,VU, HU} (B) Interrupt generation(VSEIP/VSTIP read only in hip, VSSIP - R/W) (i) VSEIP = pick_one_or_more_at_time{write hvip.VSEIP ¦¦ bit of hgeip selected by hstatus.VGEIN ¦¦ platform-specific signal(external)} (ii) VSSIP = pick_all( write hvip.VSSIP, write hip.VSSIP) (iii) VSTIP = pick_one_or_more_at_time{write hvip.VSTIP ¦¦ platform-specific signal(timer)} (iv) SGEIP = hip.sgeip is read only = bitwise-logical & [ hgeip.i && hgeie.i ] . If GEILEN is nonzero, GEILEN:1 is writable in hgeie, GEILEN_max = 63. Hstatus.VGEIN selects interrupt(i) in hgeip.i. hgeie selects the subset of GEI that cause a SGEI(HS-level) doesn't affect VSEIP generated using hgeip.i | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_007 | 2. Virtual Interrupts w/o delegation to VS-mode (VSEI/VSSI/VSTI) & SGEI | Cover VS-level/virtual interrupts targeted from VS/VU/HU with local interrupt disabled w/o delegation to VS-mode. | 1. Interrupt remains pending due to corresponding local interrupt disable i.e. [hie.vs*ie ¦¦ hgeie.i/hie.sgeie ]= 0 2. No Delegation to VS-mode : Hideleg.[10,6,2] = {0,0,0} Randomize with (i) global interrupt enable = pick_all{sstatus.sie =1,0} (ii) interrupt pending = pick_all{hip.sgeip, hip.vseip, hip.vssip, hip.vstip} using all generation methods of all 4 interrupts. (iii) Priv_Mode = pick_all{VS,VU, HU} | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_008 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from M/HS/HU-mode with delegation to VS-mode | 1. Interrupt remains pending due to corresponding delgation i.e. hideleg[10,2,6]= 1 from HS-mode to VS-mode. Randomize with (i) global interrupt enable = pick_all{vsstatus.sie =1,0} (ii) local interrupt enable = pick_all{vsie.seie, vsie.ssie, vsie.stie} (ii) interrupt pending = pick_allhip.vseip, hip.vssip, hip.vstip} using all generation methods of all 3 interrupts. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_009 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from VS-mode with both VS-mode global & local interrupt enabled and delegation to VS-mode | 1. Interrupt is serviced in VS-mode due to corresponding delgation i.e. hideleg[10,2,6]= 1 : (i) VS-mode global interrupt enable i.e. vsstatus.sie =1 (ii) && local interrupt enable i.e. [pick_any{vsie.seie, vsie.ssie, vsie.stie} =1] (iii) with corresponding interrupt pin pending i.e.[pick_any{vsip.seip, vsip.ssip, vsip.stip}=1] 2. Check Scause [9,5,1] (actually Vscause) Randomize with Interrupt generation(VSEIP/VSTIP read only in hip, VSSIP - R/W) (i) VSEIP = pick_one_or_more_at_time{write hvip.VSEIP ¦¦ bit of hgeip selected by hstatus.VGEIN ¦¦ platform-specific signal(external)} (ii) VSSIP = pick_all( write hvip.VSSIP, write hip.VSSIP) (iii) VSTIP = pick_one_or_more_at_time{write hvip.VSTIP ¦¦ platform-specific signal(timer)} Bringup: pick{vsie.ssie = 1, hip.vssip = 1(csr write in HS-mode) -> vsip.ssip = 1, vsstatus.sie = 1, hideleg[2]= 1, sstatus.spp = S-mode} Note: In VS-mode, accessing S-mode CSRs is equivalent to accessing VS-mode CSrs. Direct Access to VS-mode CSRs is not possible. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_010 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from VS-mode with VS-mode global interrupt enabled & local interrupt disabled and delegation to VS-mode | 1. Interrupt remains pending though delegated i.e. hideleg[10,2,6]= 1 from HS-mode to VS-mode & VS-mode global interrupt enable i.e. vsstatus.sie =1 however corresponding s-mode local interrupt disable i.e. vsie.s*ie= 0 Randomize with (i) interrupt pending = pick_all{vsip.seip, vsip.ssip, vsip.stip} using all generation methods of all 3 interrupts. Note: In VS-mode, accessing S-mode CSRs is equivalent to accessing VS-mode CSrs. Direct Access to VS-mode CSRs is not possible. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_011 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from VS-mode with VS-mode global interrupt disabled and delegation to VS-mode | 1. Interrupt remains pending though delegated i.e. hideleg[10,2,6]= 1 from HS-mode to VS-mode but VS-mode global interrupt enable i.e. vsstatus.sie =0 Randomize with (i) local interrupt enable = pick_all{vsie.seie, vsie.ssie, vsie.stie} (ii) interrupt pending = pick_all{vsip.seip, vsip.ssip, vsip.stip} using all generation methods of all 3 interrupts Note: In VS-mode, accessing S-mode CSRs is equivalent to accessing VS-mode CSrs. Direct Access to VS-mode CSRs is not possible. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_012 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from VU-mode with local interrupt enabled and delegation to VS-mode | 1. Interrupt is serviced in VS-mode due to corresponding delegation i.e. hideleg[10,2,6]= 1 (mode_transfer: VU to VS): (i) VS-mode local interrupt enable i.e. pick_any{vsie.seie, vsie.ssie, vsie.stie} =1] (ii) with corresponding interrupt pin pending i.e. [pick_any{vsip.seip, vsip.ssip, vsip.stip} = 1] 2. Check Scause [9,5,1] (actually Vscause) Randomize with (A) VS-mode global interrupt enable = pick_all{vsstatus.sie =1,0} (B) Interrupt generation(VSEIP/VSTIP read only in hip, VSSIP - R/W) (i) VSEIP = pick_one_or_more_at_time{write hvip.VSEIP ¦¦ bit of hgeip selected by hstatus.VGEIN ¦¦ platform-specific signal(external)} (ii) VSSIP = pick_all( write hvip.VSSIP, write hip.VSSIP) (iii) VSTIP = pick_one_or_more_at_time{write hvip.VSTIP ¦¦ platform-specific signal(timer)} Bringup: pick{vsie.stie = 1, vsip.stip using external platform source, vsstatus.sie = 1, hideleg[6]= 1, U-mode} Note: In VS-mode, accessing S-mode CSRs is equivalent to accessing VS-mode CSrs. Direct Access to VS-mode CSRs is not possible. | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_013 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from HU-mode with local interrupt enabled and delegation to VS-mode (Interrupt Injection) | VS-interrupts are disabled in HU-mode. Thus, it is equivalent to interrupt occurence in HS-mode | [7 empty] | Coded
SID_HINTR_014 | 3. Virtual Interrupts delgated to VS-mode (VSEI/VSSI/VSTI) | Cover VS-level/virtual interrupts targeted from VU-mode with local interrupt disabled and delegation to VS-mode | 1. Interrupt remains pending though delgated i.e. hideleg[10,2,6]= 1 from HS-mode to VS-mode but VS-mode local interrupt enable i.e. [pick_all{vsie.seie, vsie.ssie, vsie.stie} = 0 Randomize with (i) interrupt pending = pick_all{vsip.seip, vsip.ssip, vsip.stip} using all generation methods of all 3 interrupts (ii) VS-mode global interrupt enable = pick_all{vsstatus.sie =1,0} (iii) Privilege_mode = pick_all{VU, HU} | Riescue-D Dtest | Arch Coverage | [5 empty] | Coded
SID_HINTR_015 | 4. Virtual Interrupts During Mode Switching Transition | Cover occurrence of virtual interrupts during all mode switching process e.g. MRET, SRET, ECALL, etc | Target interrupts when the hart switches mode mode switching = pick_all{VU->VS, VS->VU, VS->HS,HS->VS, VU->HS, HS->VU, VU->M, M->VU, VS->M, M->VS, HS->M, M->HS)} interrupts = pick_all{SGEI, VSEI, VSSI, VSTI} with prerequisite Bringup: Target VSEI during SRET instruction execution (HS->VS) | Exerciser? | uArch Cov ?
SID_HINTR_016 | 4. Virtual Interrupts During Mode Switching Transition | Cover occurrence of virtual interrupts of Interrupt for one Guest ID & HS-switches to another Guest ID | Target interrupts to any Guest ID & Hypervisor switches to another Guest ID 1. Interrupted Guest_ID = pick_any {0, (2^max)-1} 2. Mode Switching = pick_any{[0, (2^max)-1] exclude Interrupted Guest ID} Bringup: Target VSEI to GuestID 0 & switch to VS-mode for GuestID max value
SID_HINTR_017 | 5. Virtual Interrupts Priority Check | Check priority order for simultaneous virtual interrupts. | interrupts = pick_all{[priority order: SEI, SSI, STI, SGEI, VSEI, VSSI, VSTI } privilege mode = pick_all{M, HS, VS,VU} Bringup: Assert STIP, VSEIP, VSSIP VSTIP pending at the same cycle for priority evaluation | Exerciser? | uArch Cov ? | [5 empty] | Coded
SID_HINTR_018 | 5. Virtual Interrupts Priority Check | Check Priority order for any Interrupts collided with Traps & Exceptions at any privilege mode | interrupts = pick_atleast_one_of_each{[Interrupts] > [Exceptions/Traps]} privilege mode = pick_all{M,HS,VS,VU} | Exerciser? | uArch Cov ?
SID_HINTR_019 | 6. Nested Virtual Interrupts (uarch) | Cover Nested interrupts (at interval other than priority evaluation at RE1 stage) across different privilege modes. 1. Occurence of another interrupt while existing interrupt is being serviced after its priority evaluation(RE1) : # RE1-->RE4 (during csr updates) # Flush : Bad Path of existing Interrupt # Trap Handling sequence #Handler routine of existing Interrupt. | 1. Occurence of another interrupt while existing interrupt is being serviced after its priority evaluation(RE1) : # RE1-->RE4 (during csr updates) # Flush : Bad Path of existing Interrupt # Trap Handling sequence #Handler routine of existing Interrupt. Randomize using random generators?? (Spec Clarity) | Exerciser? Custom Snippet | Uarch Cov?
SID_HINTR_020 | 7. Exception X Virtual Interrupts (uarch) | Cover collision of Interrupts with Exceptions Feature. Cases 1. Exception occurs inside an Interrupt Service Routine (anywhere) 2. Interrupt targeted during Exception handling. 3. Interrupt targeted during ECALL sequence | To be pushed to unit ? Callout? Needs to be highlighted to Unit. Checks? All Virtual Exceptions Cases(mcause) X Virtual Interrupts (mcause) : Must be Covered | Exerciser? | uArch Cov ?
SID_HINTR_021 | 8. Virtual Interrupts Crosses | 1. Interesting Cases with microcoded instruction (uarch) 2. Interesting Cases with Branches (conditional/unconditional) (uarch) 3. Interesting Cases with Other Redirects/Flushes (uarch) 4. Interrupts X Vectors (Callout) 5. Interrupts X CSRs 6. Cases of Debug Mode(Callout) 7. Cases of NMI, Reset, WFI | uarchitecturally similar to non hypervisor interrupts. |  | Covered in cross features (arch cov)
Generation:
IMSIC -> SGEIP, VSEIP
SSTC -> VSTIP
HVIP -> VSEIP, VSTIP, VSSIP
HIP -> VSSIP
VSIP -> VSSIP (hideleg.VSSIP=1)

## Hypervisor_x_InterruptFiltering (hidden)
Scenario details | [6 empty] | Dependencies - Timelines (Except RTL, rest of the fields to be filled in by dependent teams; Sample details filled in for example purpose) |  |  | Development Status (filled in by TP team) |  |  | Regression Status (auto-populated)
Scenario ID | Scenario Category | Scenario description | Additional details on scenarios | Stimulus Type | Coverage Type | Details on Dependency | RTL (Comes from "Milestone and Metrics Excel sheet - Bringup Tracker") | Unit TB | Dependency | Stimulus | Coverage | Bringup | Stimulus | Coverage
SID_HYP_INTRFILT_001 | Accessibility | hvien, hvip -> {M, HS} vsie, vsip -> {M, HS, VS} | hideleg[13] is read-only zero | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_002 | vsie, vsip read-only zero | hideleg[13]=0, hvien[13]=0 | hideleg[13] is read-only zero | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_003 | Writabililty | - Bits 0 to 12 of hvien are read-only zeros, for any bit in 63-13, if hvien is read-only zero then corresponding bit in hvip should also be read-only zero. - When a bit in 63-13 set in hvien, makes same bit position in vsie writable | Currently, hvien bit 13 is writable hence 63-14 are ROZ, hence same goes for hvip and vsie. | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_004 | Aliasing | For a bit in 63-13 set in hvien, corresponding bit position of vsip aliases hvip. | When hvien[13]=1, vsip[13] aliases hvip[13] | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_005 | UNSPECIFIED | For a bit in 63-13 hvien transits from 0 to 1, corresponding bit in vsie becomes UNSPECFIED | When hvien[13]= 0 -> 1: vsie[13] is UNSPECIFIED | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_006 | Virtual LCOFI pending but not enabled | hideleg[13]=0, hvien[13]=1: - hvip[13]=1, vsip[13] =1, vsie[13]=0, vsstatus.sie=0 - hvip[13]=1, vsip[13] =1, vsie[13]=1, vsstatus.sie=0 - hvip[13]=1, vsip[13] =1, vsie[13]=0, vsstatus.sie=1 |  | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_007 | Virtual LCOFI taken | hideleg[13]=0, hvien[13]=1, hvip[13]=1, vsstatus.sie = 1, then vsip[13]=1, vsie[13] = 1 -Mode: VS -> VS -Mode: VU -> VS | - CSRs set/reset in higher mode, jump to VS Mode - vscause should be 13 - vstopi = 0xD0001 - Interrupt cleared by clearing sip[13] | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_008 | Virtual LCOFI pending, not serviced | hideleg[13]=0, hvien[13]=1, hvip[13]=1, vsstatus.sie = 1, then vsip[13]=1, vsie[13] = 1 -Mode: {M, HS, HU}, not taken till mode becomes VS | If no interrupt at VS level pending other than LCOFI then: vstopi = 0xD0001 | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_009 | Virtual LCOFI pending and enabled at HS Mode, taken at VS Mode | hideleg[13]=0, hvien[13]=1, hvip[13]=1, vsip[13]=1, vsie[13] = 1, vsstatus.sie = 0 at HS Mode. In VS mode, interrupt taken when vsstatus.sie changed to 1 | - vscause should be 13 - Interrupt cleared by clearing sip[13] in VS Mode | Randoms, Dtests | CoreArchCoverage
SID_HYP_INTRFILT_010 | Virtual LCOFI priority check | Assert LCOFI at VS mode along with multiple interrupts to assert priority check, with all other interrupts across all modes: {M, HS, HU, VS, VU} |  | Randoms, Dtests | CoreArchCoverage

## Hvictl (hidden)
Scenario details | [6 empty] | Dependencies - Timelines (Except RTL, rest of the fields to be filled in by dependent teams; Sample details filled in for example purpose) |  |  | Development Status (filled in by TP team) |  |  | Regression Status (auto-populated)
Scenario ID | Scenario Category | Scenario description | Additional details on scenarios | Stimulus Type | Coverage Type | Details on Dependency | RTL (Comes from "Milestone and Metrics Excel sheet - Bringup Tracker") | Unit TB | Dependency | Stimulus | Coverage | Bringup | Stimulus | Coverage
SID_HVICTL_VTI_001 | HVICTL CSR Read/Write | Cover all fields of hvictl csr read & writes in HS-mode | [T1] Verify WARL behavior of hvictl — write various legal and illegal values. [T2] Confirm reserved bits always read as 0 regardless of written value. [T3] Check that hvictl fields (IID, DPR, IPRIOM, IPRIO, VTI) hold their values post-write when legal. | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_002 | Virtual Instruction Exception | When bit VTI (Virtual Trap Interrupt control) = 1, attempts from VS-mode cause virtual instruction exception | [T4] Attempt to read/write sip from VS-mode – should raise virtual instruction exception. [T5] Attempt to read/write sie from VS-mode – should raise virtual instruction exception. [T6] Attempt to write stimecmp should raise exception. Attempt to read stimecmp should NOT raise exception. | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_003 | Virtual Instruction Exception | When bit VTI (Virtual Trap Interrupt control) = 1, attempts to modify VSIP indirectly (except SEIP) cause virtual instruction exception Special Case | [T7] Attempt to write to any CSR that could ever cause a vsip bit (excluding bit 9, SEIP) to go from 1 → 0 or any value (0->0m 0->1, 1->1): Even if this write doesn’t cause it, exception is still raised 1. vstimecmp effect on STI 2. sip (guest sees vsip) - standard local interrupts (major identities 13–23 and 32–47) - software interrupts (SSI). Note - no exception if VSIP.SEIP is modified by IMSIC | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_004 | Vstopi | Candidate 1: vsip[9] and vsie[9] = 1, hstatus.VGEIN = [1,5], vstopie !=0 | vstopi.IID = 9 vstopi.IPRIO = vstopei.IID interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_005 | Vstopi | Candidate 2: vsip[9] and vsie[9] = 1, hstatus.VGEIN = 0, hvictl.IID = 9, hvictl.IPRIO != 0 | vstopi.IID = 9 vstopi.IPRIO = vstopei.IID interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_006 | Vstopi | Candidate 3: vsip[9] and vsie[9] = 1, (vstopei=0 or hvictl.IID = 9 or hvictl.IPRIO != 0) | vstopi.IID = 9 vstopi.IPRIO = 255 interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_007 | Vstopi | Candidate 4: hvictl.VTI = 0, | vstopi.IID = 9 vstopi.IPRIO = vstopei.IID interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_008 | Vstopi | Candidate 5: hvictl.VTI = 1, hvictl.IID != 9 | vstopi.IID = hvictl.IID vstopi.IPRIO = vstopei.IID if [1,255] if 0, decided based on DPR interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_008 | Vstopi | No candidate satifies: hvictl.VTI = 1, hvictl.IID == 9, ((vsip[9] and vsie[9] != 1, hstatus.VGEIN = 0 or vstopie ==0) or hvictl.IPRIO == 0) | vstopi.IID = hvictl.IID vstopi.IPRIO = 1 interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_008 | Vstopi | if hvictl.IPRIOM = 0, vstopi.IPRIO = 1, cross this all candidates | vstopi.IID = hvictl.IID vstopi.IPRIO = 1 interrupt priority based on DPR interrupt taken with correct cause in VS mode only when enabled | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_008 | Priority of these interrupts with other VS and non-VS mode interrupts
# |  | Scenario | Setup (CSRs) | Stimulus | Expected | Assembly Test(s)
1 | Virtual Interrupts | Inject via HV‑control (IID≠9) | hvictl.VTI=1, hvictl.IID=13, hvictl.IPRIO=13, hvictl.DPR=1 hvip[2,6]=1 ,hie[2,6]=1 ,vsip[1,5]=1 ,vsie[1,5]=1 | trap to VS‑mode | vstopi.iid == 13, vstopi.iprio == 13 | test1
2 | Virtual Interrupts | No interrupt if hvictl.IID=9 & IPRIO=0 | hvictl.VTI=1, hvictl.IID=9, hvictl.IPRIO=0 | trap to VS‑mode | no interrupt (vstopi==0), execution continues to ecall | test2
5 | Virtual Interrupts | Simultaneous interrupt with DPR=1 | hvictl.VTI=1, hvictl.IID=13 (IID!=9), hvictl.IPRIO=13, hvictl.DPR=0 Also hvip.VSEIP=1, vsie.VSEIE=1 | IID=13 > VSEIP priority | IID=13 > VSEIP priority | test3
6 | Virtual Interrupts | Simultaneous interrupt with DPR=0 | hvictl.VTI=1, hvictl.IID=13 (IID!=9), hvictl.IPRIO=13, hvictl.DPR=1 Also hvip.VSEIP=1, vsie.VSEIE=1 | IID=13 < VSEIP priority | IID=13 < VSEIP priority | test4
7 | Cross other scenarios with hvictl.vti=1
Test ID | Possible Cross Scenario (TBD) | hvictl.VTI | hvictl.IID | hvictl.IPRIO | hvictl.DPR | hstatus.VGEIN | vstopei | vsip[9] / vsie[9] | Expected | Trap Taken to VS-mode? | Remarks
vstopi
VT01 | Guest SEI via guest file | 0 or 1 | — | — | — | ≠0 | 0x10 | 1,1 | IID=9, IPRIO=vstopei | Yes | Top priority source
VT02 | Guest SEI via hvictl | 1 | 9 | 0x30 | X | 0 | 0 | 1,1 | IID=9, IPRIO=0x30 | Yes | Uses hvictl IPRIO
VT03 | Guest SEI fallback | 1 | 5 | 0x20 | 1 | 0 | 0 | 1,1 | IID=9, IPRIO=256 | Yes | Default fallback
VT04 | hvictl injects major interrupt | 1 | 21 | 0x40 | 0 | X | X | X | IID=21, IPRIO=0x40 | Yes | Takes precedence over vsip bits
VT05 | hvictl injects SEI with IPRIO=0 | 1 | 9 | 0 | X | 0 | 0 | 1,1 | vstopi = 0 | No | Indicates “no interrupt”
VT06 | VTI = 0, standard vsip/vsie | 0 | — | — | — | X | X | vsip=0x22, vsie=0x22 | Highest in vsip&vsie | Yes | Uses hviprio[1/2] priority
VT07 | Conflicting sources, SEI wins | 1 | 12 | 0x40 | 1 | 0 | 0 | vsip[9]=1, vsie[9]=1 | IID=9, IPRIO=256 | Yes | SEI priority over lower DPR
VT08 | Conflicting, DPR wins | 1 | 12 | 0x40 | 0 | 0 | 0 | vsip[9]=1, vsie[9]=1 | IID=12, IPRIO=0x40 | Yes | DPR=0 overrides SEI
VT09 | IPRIOM=0 → IPRIO=1 | 1 | 33 | X | X | — | — | — | IPRIO=1 | Yes | Test IPRIOM=0 fallback
VT10 | IPRIOM=1, valid IPRIO | 1 | 33 | 0x20 | X | — | — | — | IPRIO=0x20 | Yes | Valid full priority range
VT11 | IPRIOM=1, IPRIO > 255 | 1 | 33 | 0x300 | X | — | — | — | IPRIO=255 | Yes | Capped per spec
VT12 | vsip = vsie = 0 | X | X | X | X | — | — | 0/0 | vstopi=0 | No | No interrupt condition
VT13 | Trap only if vsstatus.SIE=1 | 1 | 11 | 0x30 | 1 | — | — | — | vstopi≠0, no trap if SIE=0 | No | Tests privilege control
VT14 | Trap from VU-mode | 1 | 15 | 0x50 | 1 | — | — | — | vstopi=15 | Yes | VU traps to VS allowed
VT15 | WARL limit: IID=max supported | 1 | 63 | 0x20 | 1 | — | — | — | vstopi=63 | Yes | Upper IID bound
Special Case | Case of HVICTL.VTI=1, IID!=9
List of Scenarios to be covered in coverage coding |  |  | Coverage Name
1 | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, vstopei!=zero (ensure IMSIC based interrupt is pending in form of VSEIP delegated to VS-mode) |  | vstopi_candidate_1
2 | vsip[9]=1, vsie[9]=1, hstatus.VGEIN=0, hvictl.IID = 9 and hvictl.IPRIO != 0 |  | vstopi_candidate_2
3A | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, vstopei=zero |  | vstopi_candidate_3
3B | vsip[9]=1, vsie[9]=1, hstatus.VGEIN={zero, non-zero}, hvictl.IID = 9, hvictl.IPRIO=0
3C | vsip[9]=1, vsie[9]=1, hstatus.VGEIN={zero, non-zero} hvictl.IID != 9, hvictl.IPRIO (any)
3D | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, hvictl.IID = 9, hvictl.IPRIO!=0
4 | hvictl.VTI=0, pick_atleast_one_of[{vsip[1]=1, vsie[1]=1}, {vsip[5]=1, vsie[5]=1}, {vsip[13]=1, vsie[13]=1}
5 | hvictl.VTI=1, hvictl.IID!=9 (cover all value except 9), randomise hvictl.DPR={0,1}, IPRIO=All values, IPRIOM={0,1}
6A | hvictl.VTI=1, hvictl.IID=9, randomise hvictl.DPR={0,1}, IPRIO=All values, IPRIOM={0,1} | vstopi=0 case
6B | hvictl.IID=9, IPRIO=0 randomise other fields of hvictl | vstopi=0 case
Cross | pick_one_of{1,2,3A,3B,3C,3D} crossed with pick_one_of{4,5} | Note: A. 1,2,3 are mutually exclusive of each other B. 4,5 are mutually exclusive of each other
Vstopi CSR | All IID & All IPRIO coverage
hvictl CSR | The format of hvictl is: bit 30 bits 27:16 bit 9 bit 8 bits 7:0 VTI IID (WARL) DPR IPRIOM IPRIO
VSCAUSE CSR | VSCAUSE[62:0] should cover all ranges as supported by VSTOPI.IID

## hvictl.vti=1 (old) (hidden)
Scenario details | [6 empty] | Dependencies - Timelines (Except RTL, rest of the fields to be filled in by dependent teams; Sample details filled in for example purpose) |  |  | Development Status (filled in by TP team) |  |  | Regression Status (auto-populated)
Scenario ID | Scenario Category | Scenario description | Additional details on scenarios | Stimulus Type | Coverage Type | Details on Dependency | RTL (Comes from "Milestone and Metrics Excel sheet - Bringup Tracker") | Unit TB | Dependency | Stimulus | Coverage | Bringup | Stimulus | Coverage
SID_HVICTL_VTI_001 | HVICTL CSR Read/Write | Cover all fields of hvictl csr read & writes in HS-mode | [T1] Verify WARL behavior of hvictl — write various legal and illegal values. [T2] Confirm reserved bits always read as 0 regardless of written value. [T3] Check that hvictl fields (IID, DPR, IPRIOM, IPRIO, VTI) hold their values post-write when legal. | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_002 | Virtual Instruction Exception | When bit VTI (Virtual Trap Interrupt control) = 1, attempts from VS-mode cause virtual instruction exception | [T4] Attempt to write sip from VS-mode – should raise virtual instruction exception. [T5] Attempt to write sie from VS-mode – should raise virtual instruction exception. [T6] Attempt to write stimecmp should raise exception. | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_003 | Virtual Instruction Exception | When bit VTI (Virtual Trap Interrupt control) = 1, attempts to modify VSIP indirectly (except SEIP) cause virtual instruction exception Special Case | [T7] Attempt to write to any CSR that could ever cause a vsip bit (excluding bit 9, SEIP) to go from 1 → 0 or any value (0->0m 0->1, 1->1): Even if this write doesn’t cause it, exception is still raised 1. vstimecmp effect on STI 2. sip (guest sees vsip) - standard local interrupts (major identities 13–23 and 32–47) - software interrupts (SSI). Note - no exception if VSIP.SEIP is modified by IMSIC | Riescue-D Dtest | Arch Coverage
SID_HVICTL_VTI_004 | Virtual Instruction Exception | When bit VTI (Virtual Trap Interrupt control) = 1, attempts to modify VSIP indirectly (except SEIP) cause virtual instruction exception Special Case | [T7] Attempt to write to any CSR that could ever cause a vsip bit (excluding bit 9, SEIP) to go from 1 → 0 or any value (0->0m 0->1, 1->1): Even if this write doesn’t cause it, exception is still raised 1. vstimecmp effect on STI 2. sip (guest sees vsip) - standard local interrupts (major identities 13–23 and 32–47) - software interrupts (SSI). Note - no exception if VSIP.SEIP is modified by IMSIC | Riescue-D Dtest | Arch Coverage
# |  | Scenario | Setup (CSRs) | Stimulus | Expected | Assembly Test(s)
1 | Virtual Interrupts | Inject via HV‑control (IID≠9) | hvictl.VTI=1, hvictl.IID=13, hvictl.IPRIO=13, hvictl.DPR=1 hvip[2,6]=1 ,hie[2,6]=1 ,vsip[1,5]=1 ,vsie[1,5]=1 | trap to VS‑mode | vstopi.iid == 13, vstopi.iprio == 13 | test1
2 | Virtual Interrupts | No interrupt if hvictl.IID=9 & IPRIO=0 | hvictl.VTI=1, hvictl.IID=9, hvictl.IPRIO=0 | trap to VS‑mode | no interrupt (vstopi==0), execution continues to ecall | test2
5 | Virtual Interrupts | Simultaneous interrupt with DPR=1 | hvictl.VTI=1, hvictl.IID=13 (IID!=9), hvictl.IPRIO=13, hvictl.DPR=0 Also hvip.VSEIP=1, vsie.VSEIE=1 | IID=13 > VSEIP priority | IID=13 > VSEIP priority | test3
6 | Virtual Interrupts | Simultaneous interrupt with DPR=0 | hvictl.VTI=1, hvictl.IID=13 (IID!=9), hvictl.IPRIO=13, hvictl.DPR=1 Also hvip.VSEIP=1, vsie.VSEIE=1 | IID=13 < VSEIP priority | IID=13 < VSEIP priority | test4
7 | Cross other scenarios with hvictl.vti=1
Test ID | Possible Cross Scenario (TBD) | hvictl.VTI | hvictl.IID | hvictl.IPRIO | hvictl.DPR | hstatus.VGEIN | vstopei | vsip[9] / vsie[9] | Expected | Trap Taken to VS-mode? | Remarks
vstopi
VT01 | Guest SEI via guest file | 0 or 1 | — | — | — | ≠0 | 0x10 | 1,1 | IID=9, IPRIO=vstopei | Yes | Top priority source
VT02 | Guest SEI via hvictl | 1 | 9 | 0x30 | X | 0 | 0 | 1,1 | IID=9, IPRIO=0x30 | Yes | Uses hvictl IPRIO
VT03 | Guest SEI fallback | 1 | 5 | 0x20 | 1 | 0 | 0 | 1,1 | IID=9, IPRIO=256 | Yes | Default fallback
VT04 | hvictl injects major interrupt | 1 | 21 | 0x40 | 0 | X | X | X | IID=21, IPRIO=0x40 | Yes | Takes precedence over vsip bits
VT05 | hvictl injects SEI with IPRIO=0 | 1 | 9 | 0 | X | 0 | 0 | 1,1 | vstopi = 0 | No | Indicates “no interrupt”
VT06 | VTI = 0, standard vsip/vsie | 0 | — | — | — | X | X | vsip=0x22, vsie=0x22 | Highest in vsip&vsie | Yes | Uses hviprio[1/2] priority
VT07 | Conflicting sources, SEI wins | 1 | 12 | 0x40 | 1 | 0 | 0 | vsip[9]=1, vsie[9]=1 | IID=9, IPRIO=256 | Yes | SEI priority over lower DPR
VT08 | Conflicting, DPR wins | 1 | 12 | 0x40 | 0 | 0 | 0 | vsip[9]=1, vsie[9]=1 | IID=12, IPRIO=0x40 | Yes | DPR=0 overrides SEI
VT09 | IPRIOM=0 → IPRIO=1 | 1 | 33 | X | X | — | — | — | IPRIO=1 | Yes | Test IPRIOM=0 fallback
VT10 | IPRIOM=1, valid IPRIO | 1 | 33 | 0x20 | X | — | — | — | IPRIO=0x20 | Yes | Valid full priority range
VT11 | IPRIOM=1, IPRIO > 255 | 1 | 33 | 0x300 | X | — | — | — | IPRIO=255 | Yes | Capped per spec
VT12 | vsip = vsie = 0 | X | X | X | X | — | — | 0/0 | vstopi=0 | No | No interrupt condition
VT13 | Trap only if vsstatus.SIE=1 | 1 | 11 | 0x30 | 1 | — | — | — | vstopi≠0, no trap if SIE=0 | No | Tests privilege control
VT14 | Trap from VU-mode | 1 | 15 | 0x50 | 1 | — | — | — | vstopi=15 | Yes | VU traps to VS allowed
VT15 | WARL limit: IID=max supported | 1 | 63 | 0x20 | 1 | — | — | — | vstopi=63 | Yes | Upper IID bound
Special Case | Case of HVICTL.VTI=1, IID!=9
List of Scenarios to be covered in coverage coding |  |  | Coverage Name
1 | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, vstopei!=zero (ensure IMSIC based interrupt is pending in form of VSEIP delegated to VS-mode) |  | vstopi_candidate_1
2 | vsip[9]=1, vsie[9]=1, hstatus.VGEIN=0, hvictl.IID = 9 and hvictl.IPRIO != 0 |  | vstopi_candidate_2
3A | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, vstopei=zero |  | vstopi_candidate_3
3B | vsip[9]=1, vsie[9]=1, hstatus.VGEIN={zero, non-zero}, hvictl.IID = 9, hvictl.IPRIO=0
3C | vsip[9]=1, vsie[9]=1, hstatus.VGEIN={zero, non-zero} hvictl.IID != 9, hvictl.IPRIO (any)
3D | vsip[9]=1, vsie[9]=1, hstatus.VGEIN!=0, hvictl.IID = 9, hvictl.IPRIO!=0
4 | hvictl.VTI=0, pick_atleast_one_of[{vsip[1]=1, vsie[1]=1}, {vsip[5]=1, vsie[5]=1}, {vsip[13]=1, vsie[13]=1}
5 | hvictl.VTI=1, hvictl.IID!=9 (cover all value except 9), randomise hvictl.DPR={0,1}, IPRIO=All values, IPRIOM={0,1}
6A | hvictl.VTI=1, hvictl.IID=9, randomise hvictl.DPR={0,1}, IPRIO=All values, IPRIOM={0,1} | vstopi=0 case
6B | hvictl.IID=9, IPRIO=0 randomise other fields of hvictl | vstopi=0 case
Cross | pick_one_of{1,2,3A,3B,3C,3D} crossed with pick_one_of{4,5} | Note: A. 1,2,3 are mutually exclusive of each other B. 4,5 are mutually exclusive of each other
Vstopi CSR | All IID & All IPRIO coverage
hvictl CSR | The format of hvictl is: bit 30 bits 27:16 bit 9 bit 8 bits 7:0 VTI IID (WARL) DPR IPRIOM IPRIO
VSCAUSE CSR | VSCAUSE[62:0] should cover all ranges as supported by VSTOPI.IID